# CISC 699 — Hard Stop 1: Proposal Approval Package

Project title: Placement as Schema — A GraphQL Federation Layer with Backend Placement Declared in the Type System, and the Workload Point Where Federation Stops Paying

Student: Jai Behl

Supervisor: Majid Shaalan, Ph.D.

Submitted: 9/13/2026

Repository: https://github.com/ciel57142-wq/CISC699.git

Document version: v0.1

## Contents

- AI Usage Log and Academic Integrity

- Background

- Problem Statement, Objectives, and Intended Artifact

- Success Criteria

- Scope Boundaries

- Technical Approach — Machine, Architecture, Computational, API

- Project Plan

- Work Breakdown Structure

- Assumptions, Constraints, and Risks

- Revision Record — Supervisor Feedback Substitute

- Open Supervisor Decisions

- One-Page Approval Brief

- References

## 1. AI Usage Log and Academic Integrity

### 1.1 Disclosure statement

I used a generative AI assistant (Claude, Anthropic) as a drafting and structuring aid in preparing this proposal package. The use was substantial and is itemized below. All technical decisions, all scope boundaries, all risk judgments, and all claims about feasibility are mine, and I am accountable for them. Where the assistant proposed a design choice, I reviewed it and either adopted it, modified it, or rejected it; the adopted ones are mine now regardless of origin.

I have not used AI to fabricate results, measurements, citations, or evidence. No number in this document is a measurement. Every quantitative target in §4 is a provisional threshold to be tested, and every one is labeled as such.

### 1.2 Itemized log

| # | Date | Tool | Task | Nature of use | My verification |
| --- | --- | --- | --- | --- | --- |
| 1 | 9/13 | Claude (Anthropic) | Topic selection | Discussed several candidate projects; challenged the viability of this one | Chose the topic myself against the assistant’s stated reservations; the reasoning is in §3.2 |
| 2 | 9/13 | Claude (Anthropic) | Competitive landscape | Identified Hasura DDN and GraphQL Mesh as prior art I had not been aware of | Read the NDC specification and Hasura architecture docs directly; §2.3 is my own reading |
| 3 | 9/13 | Claude (Anthropic) | This proposal | Drafting of document structure, WBS, risk register phrasing, dependency table | Reviewed every section; set the §4 thresholds myself; changed |
| 4 | 9/13 | Claude (Anthropic) | Annotated bibliography | Suggested candidate sources with author, title, venue, year |  |

### 1.3 What was not AI-assisted

### 1.4 Academic integrity attestation

This package represents my own project, scope decisions, and technical judgment. AI assistance is disclosed above in the form and detail required. I understand that I am responsible for defending every technical claim in this document in the recorded walkthrough and in supervision meetings.

Signed: Jai Behl — 09/13

## 2. Background

### 2.1 Polyglot persistence and the cost it defers

Production data architectures are rarely single-engine. The prevailing practice — polyglot persistence — places each entity in the store whose data model fits it: transactional records in a relational engine, semi-structured documents in a document store, relationships in a graph store, ephemeral state in a key–value store. Stonebraker and Çetintemel’s argument that specialized engines outperform general-purpose ones on their own workloads is the intellectual origin of this practice, and it has largely won in industry.

It won at a cost that is deferred rather than avoided. Once entities live in different engines, any question that spans them becomes application code. A developer queries store A, queries store B, pulls both result sets into application memory, and joins them by hand. That code is untested against a correctness oracle, it moves far more data across the network than the answer requires, and it is rewritten for every new cross-store question.

### 2.2 Federation as the industrial response

The industrial response is federation: a middleware layer that accepts one query, plans across multiple backends, pushes work down to each engine where possible, and combines the partial results. The academic lineage runs through BigDAWG’s islands of information and CloudMdsQL; the production lineage runs through Apache Calcite and Trino on the SQL side and Hasura and GraphQL Mesh on the GraphQL side.

What the literature documents less clearly is the boundary condition. Federation is not free. The middleware cannot use backend indexes for the join, it pays serialization costs on every partial result, and it lacks the cross-store statistics a single-engine optimizer takes for granted. The competing option is consolidation: move everything into one sufficiently general engine, typically PostgreSQL with JSONB, and accept a worse data-model fit in exchange for a real optimizer. Practitioners choose between these two by intuition.

### 2.3 Where the existing systems put placement — and why that matters

Hasura’s current architecture is the closest prior art to this project and must be addressed directly rather than avoided. Its engine does not query data sources at all: it compiles an incoming GraphQL operation into an intermediate representation and dispatches that IR to a data connector, an HTTP service conforming to the published Native Data Connector (NDC) specification, which translates the IR into the native query language of one backend and pushes filtering and sorting down into it. Relationships spanning two connectors are resolved by the engine. GraphQL Mesh occupies similar ground with a broader and shallower source list.

Both systems share a design property that this project questions. Placement — the fact that a given entity lives in MongoDB rather than PostgreSQL — is expressed in configuration that sits outside the schema. In Hasura it lives in OpenDD metadata files and subgraph definitions; in Mesh it lives in a YAML source list with handlers. The schema a developer reads and the placement they must reason about are in different artifacts.

That separation is defensible for the systems that chose it: it decouples the API contract from the physical layout, which is exactly what you want when a platform team owns placement and application teams own the schema. But it has a cost that is rarely measured. For the much more common case of a small team that owns both, the developer reading type Order { ... } cannot see that Order.customer will cross a process boundary and Order.lineItems will not. The performance-relevant fact is invisible at the point where the performance-relevant decision is made.

### 2.4 The gap this project addresses

Two gaps, one design and one empirical.

Design. No accessible federation layer makes backend placement a first-class annotation in the type definition itself, where the developer writing the query can see it. Whether that is an improvement is an open question, not an assumption — it may simply relocate complexity, and the project must be able to report that.

Empirical. There is no accessible, reproducible measurement that says for a workload shaped like yours, here is the point at which federation stops paying for itself relative to consolidation. Vendor benchmarks in this space are run by vendors on their own systems.

## 3. Problem Statement, Objectives, and Intended Artifact

### 3.1 Problem statement

Teams operating heterogeneous data stores must choose between federating queries across those stores and consolidating the data into a single general-purpose engine. The trade-off is real and workload-dependent: federation preserves data-model fit and avoids a migration, but forfeits the single-engine optimizer and pays a data-movement cost that scales with intermediate result cardinality. Practitioners currently make this choice without a reproducible empirical basis, and the tools available to them hide the placement information that would inform the choice.

The problem this project solves is not “build a better federated engine.” Hasura and Trino exist and are better than anything a solo student will write in fourteen weeks. The problem is that (a) the crossover condition has not been isolated and measured in a form a practitioner can apply to their own workload, and (b) the design question of whether placement belongs in the schema has not been tested.

### 3.2 Framing note — why build rather than adopt

This is the question a reviewer will ask first, so it is answered first.

Adopting Hasura would give a better federation layer and no ability to vary the design variable under study. The project’s design claim concerns where placement information lives; testing it requires a system in which placement lives somewhere else. A fork of a production engine is not a smaller undertaking than a minimal purpose-built one, and it carries the engine’s entire feature surface as accidental complexity.

The engine is therefore apparatus, deliberately minimal, built to make one variable movable. It is not a competitor to Hasura and the report will say so in those words. Hasura appears in the evaluation as a reference arm (§6.5, A5), which strengthens the result rather than undermining it.

A second commitment follows, and it is load-bearing: a rigorously measured negative result is a successful project. If the measurement shows consolidated PostgreSQL beats federation across most of the workload, or that schema-level placement measurably increases configuration complexity rather than reducing it, those are valid and useful findings. A student who cannot afford a negative result will bias a benchmark they control without ever intending to. Removing that pressure is the mitigation that makes every other methodological safeguard in §9 actually work. This requires supervisor agreement in writing (§11, Decision 2).

### 3.3 Objectives

Each objective maps to at least one success criterion in §4 and at least one work package in §8.

| ID | Objective | Maps to |
| --- | --- | --- |
| O1 | Design a schema annotation syntax that declares backend placement inside the GraphQL type definition, and implement the compiler that resolves it into an executable plan | SC-2, SC-6 · WP-2 |
| O2 | Implement a read-only federated execution layer over two heterogeneous backends, supporting single-store and two-store queries over a defined GraphQL operation subset | SC-1, SC-2 · WP-3, WP-5 |
| O3 | Implement predicate and projection pushdown into each backend’s native query language, and measure the data-movement reduction attributable to each | SC-3 · WP-8 |
| O4 | Build a differential correctness oracle validating every federated result against a consolidated ground-truth instance | SC-1 · WP-6 |
| O5 | Construct a reproducible benchmark harness measuring latency, bytes transferred, and intermediate cardinality across four execution arms | SC-4, SC-9 · WP-9 |
| O6 | Identify and characterize the crossover point at which federated median latency exceeds consolidated median latency, expressed as a function of a measurable workload property | SC-5 · WP-11 |
| O7 | Evaluate the configuration-complexity claim by comparing the effort required to add a new backend-resident type in this system against the equivalent operation in Hasura DDN | SC-6 · WP-10 |
| O8 | Produce a written report and reproducibility package permitting independent re-execution of every reported measurement | SC-9 · WP-13 |

### 3.4 Intended artifact

Five deliverables, submitted together:

- engine/ — the federation layer. Python, read-only. Schema loader and placement resolver, GraphQL parser, logical plan builder, rule-based rewriter, in-memory hash-join executor, pluggable backend adapters.

- oracle/ — the differential correctness harness, the consolidated PostgreSQL mirror, and the loader that keeps the two placements provably equivalent.

- bench/ — the workload, the measurement harness, raw results, config hashes, and hardware fingerprints. One command reproduces the full run.

- eval/complexity/ — the configuration-complexity study: the same schema expressed in both systems, the counting protocol, and the results.

- Report — background, method, results, crossover analysis, threats to validity, and an explicit statement of what the measurement does not support.

The artifact is a local, containerized demonstration released under a permissive open source licence. It is not a hosted service and does not attempt production readiness (§11, Decision 3).

## 4. Success Criteria

All thresholds below are provisional. They were set from the literature and from pilot reasoning, not from measurement. §7 places a baseline measurement at the midpoint hard stop; thresholds will be revised once, in writing, at that point, with the revision and its justification recorded in the repository. After that revision they are frozen. Thresholds are never adjusted after a measurement run they influence. This is the pre-registration commitment referenced in §9, R3.

| ID | Criterion | Measure | Provisional threshold | Method | Fallback if missed |
| --- | --- | --- | --- | --- | --- |
| SC-1 | Correctness | Result equivalence with the differential oracle, order-insensitive, over the full query workload | 100% of workload queries; zero unexplained divergences. Any divergence must have a documented root cause and a regression test | Automated oracle run in CI on every commit | A documented, reproducible divergence with root-cause analysis is an acceptable deliverable; an undocumented one is not |
| SC-2 | Functional coverage | Proportion of the defined GraphQL operation subset (§6.4) executable end to end | 100% of the MVA subset; ≥80% including extension operators | Conformance suite, one test per operator × backend pair | Reduce the subset and restate it explicitly; do not silently under-deliver |
| SC-3 | Pushdown effectiveness | Bytes transferred across the backend boundary, pushdown enabled vs. disabled, on selective queries (selectivity ≤10%) | ≥70% reduction in bytes transferred | Instrumented adapter byte counters; identical query, two configs | Report the achieved reduction with analysis of why the rules did not fire |
| SC-4 | Latency characterization | Median end-to-end query latency across all arms (§6.5) | Federated within 3× consolidated median on single-store queries. No threshold imposed on cross-store queries — those are the measurement | Median of 7 timed runs, 3 warm-up runs discarded, IQR reported with every median | None needed; this criterion measures rather than passes |
| SC-5 | Crossover identified | The value of the independent variable at which federated median latency crosses consolidated median latency | A crossover point reported with IQR bounds, or a substantiated finding that no crossover exists within the tested range | Parameter sweep over intermediate result cardinality, ≥6 points per curve | A well-characterized “no crossover in range, and here is why” is a valid result |
| SC-6 | Configuration complexity | Effort to add one new backend-resident type with one cross-store relationship, measured as: files touched, lines of configuration, and distinct concepts a developer must know | ≥40% reduction in files touched vs. the equivalent Hasura DDN operation, with lines and concepts reported alongside | Fixed task, both systems, protocol pre-registered in eval/complexity/PROTOCOL.md before either is measured | Report the honest number. A null or negative result here is the single most defensible finding this project can produce, because it contradicts my own design premise |
| SC-7 | Defect rate | Open defects at final submission, by severity | Zero open severity-1 (incorrect results); ≤5 open severity-2 | Issue tracker with severity labels; triage at each hard stop | Severity-1 defects block submission of the affected result, not the project |
| SC-8 | Test coverage | Line coverage on the placement resolver, planner, and pushdown modules | ≥80% | pytest --cov, reported in CI | State achieved coverage honestly in the report |
| SC-9 | Reproducibility | Proportion of reported numbers traceable to a committed run artifact | 100%. Independent re-execution from a clean checkout via one documented command | Config hash + hardware fingerprint + raw timings committed per run; clean-machine rehearsal before freeze | None. Non-negotiable. An untraceable number is withdrawn from the report |
| SC-10 | Stakeholder acceptance | Supervisor sign-off on the seven decisions in §11 | Decisions 1–3 resolved before the midpoint hard stop; all seven before final submission | Written record in docs/decisions/ | Decisions 1–3 unresolved at midpoint escalates to a scope renegotiation, not a silent continuation |

### 4.1 Operational definition of the crossover

“Crossover” is defined precisely, because an undefined crossover is the failure mode this criterion exists to prevent.

The crossover point is the value of intermediate result cardinality k — the number of rows or documents returned by the more selective side of a two-store join before the join is performed — at which the median end-to-end latency of the federated arm first exceeds the median end-to-end latency of the consolidated arm, holding query shape and both data sets constant.

The independent variable is k, varied by adjusting predicate selectivity on the driving side. It is reported with the IQR of both arms at the crossing, so that a crossing inside the noise band is reported as indeterminate rather than as a point.

### 4.2 Why configuration complexity is measured this way

SC-6 deliberately avoids a human-subjects usability study as its primary measure. A study with developer participants would be stronger evidence, but it introduces IRB review, a recruitment dependency, and a sample size a solo student cannot reach in one semester. The substitute is an objective, countable protocol on a fixed task — files touched, configuration lines, distinct concepts — with the counting rules written down and committed before either system is measured, so the protocol cannot be adjusted to favour the outcome.

A small task-based developer study (N = 8–12, time-on-task and error rate) is retained as an extension, contingent on written IRB exemption obtained by the midpoint hard stop (§11, Decision 6). If exemption is not obtained by then, the extension is cut without affecting any other deliverable.

## 5. Scope Boundaries

### 5.1 Minimum viable artifact (the floor)

If the semester goes badly, this is what still ships and still constitutes a defensible project:

- Two backends: PostgreSQL (relational) and MongoDB (document)

- Schema-level placement annotation, resolver, and validator

- Single-store and two-store queries over the MVA operation subset

- Predicate pushdown

- The differential oracle

- A measured comparison against consolidated PostgreSQL

- The configuration-complexity comparison against Hasura DDN

Everything below is above the floor and is cut in the order listed.

### 5.2 Extensions, in cut order

- Projection pushdown

- Heuristic join ordering (smallest-relation-first)

- Third backend: Redis (key–value)

- Fourth backend: Neo4j (graph)

- Three-store traversals

- Hasura DDN as a live fifth measurement arm (as opposed to a configuration-complexity comparator only)

- Developer usability study, contingent on IRB exemption

### 5.3 Explicitly out of scope

This list is the most load-bearing section of the proposal. Each item is something a reader might reasonably expect and will not receive.

| # | Out of scope |
| --- | --- |
| 1 | Mutations and writes of any kind. The engine is read-only |
| 2 | Cross-store ACID, two-phase commit, distributed consistency |
| 3 | GraphQL subscriptions and any streaming interface |
| 4 | Cost-based optimization with collected statistics |
| 5 | Authentication, authorization, row/column-level security |
| 6 | Full GraphQL surface: fragments beyond named fragments, directives beyond the placement annotation, interfaces, unions, custom scalars beyond a fixed set |
| 7 | Automatic schema introspection and generation from existing databases |
| 8 | Non-equality join conditions; traversals of depth > 2 in the MVA |
| 9 | Horizontal scale-out, sharding, multi-node deployment |
| 10 | Schema evolution and migration tooling |
| 11 | Hosted deployment, production hardening, operational tooling |
| 12 | Query result caching at the federation layer |
| 13 | Outperforming Hasura, Trino, or Calcite on any axis |
| 14 | NDC specification compliance |
| 15 | A graphical user interface or schema editor |
| 16 | More than four backends |
| 17 | Generalizing the crossover result beyond the tested workload and hardware |

## 6. Technical Approach — Machine, Architecture, Computational, API

### 6.1 Machine

| Item | Baseline |
| --- | --- |
| Development machine | Intel Core i5, NVIDIA GEforce RTX, 16 GB ram |
| Measurement protocol | Benchmark runs on an otherwise idle machine, AC power, background sync and indexing disabled, thermal steady state reached before timing |
| Container runtime | Docker Engine + Docker Compose |
| Language runtime | Python 3.12, dependencies hash-locked |
| Authoring | Markdown in-repository for all project documents; [Word/Docs] only for Canvas submission |
| Backup | Git remote (GitHub) + local snapshot |
| Planning | GitHub Issues + Milestones, one milestone per course hard stop |

Evidence to submit: proposal file, exported milestone/board view, and the git log showing dated revisions.

### 6.2 Architecture

GraphQL operation
          │
          ▼
 ┌──────────────────────────────────────────────┐
 │             Federation Engine                │
 │                                              │
 │   Schema loader ──► Placement resolver       │
 │   (@store annotations read from the SDL)     │
 │                 │                            │
 │                 ▼                            │
 │   Parser ──► Logical plan ──► Rewriter       │
 │                              (pushdown rules,│
 │                               join ordering) │
 │                 │                            │
 │                 ▼                            │
 │            Executor (hash join, in-memory)   │
 └───────┬──────────────────────┬───────────────┘
         │                      │
 ┌───────▼────────┐    ┌────────▼───────┐
 │ PostgreSQL     │    │ MongoDB        │   [+ Redis, Neo4j — extensions]
 │ adapter        │    │ adapter        │
 └───────┬────────┘    └────────┬───────┘
         │                      │
 ┌───────▼────────┐    ┌────────▼───────┐
 │  PostgreSQL    │    │   MongoDB      │
 └────────────────┘    └────────────────┘

   Same operation ──► ┌────────────────────────────┐
                      │ Consolidated PostgreSQL    │ ◄── ground truth for the
                      │ (all entities, JSONB where │     oracle, and arm A2
                      │  the model demands it)     │
                      └────────────────────────────┘

Six components, each independently testable:

- Schema loader and placement resolver — reads the annotated SDL and produces the internal placement map. This is the component under design study; it is the thing Hasura expresses as external metadata.

- Parser — GraphQL operation to logical plan. Uses a standard GraphQL parser; the annotation is a schema directive, not a language extension, so the schema remains valid GraphQL SDL and standard tooling still reads it.

- Rewriter — rule-based. Each rule is a separate, individually testable transformation with before/after plan assertions.

- Executor — in-memory hash join over partial results. Deliberately simple: a naive executor makes data-movement cost visible, which is what the project measures.

- Adapters — one per backend, translating pushed-down plan fragments into native query form and instrumenting bytes transferred.

- Consolidated mirror — not part of the engine, but part of the apparatus.

Architectural decisions are recorded as ADRs in docs/decisions/, one per choice, never edited after acceptance — superseded instead.

Evidence to submit: this diagram plus the milestone map in §7.2, attached to the proposal.

### 6.3 The design variable, stated concretely

The annotation under study looks approximately like this. Exact syntax is an open design question and will be settled in ADR-0003 during WP-2.

directive @store(name: String!, collection: String) on OBJECT | FIELD_DEFINITION

type Customer @store(name: "pg", collection: "customers") {
  id: ID!
  email: String!
  orders: [Order!]! @store(name: "mongo")
}

type Order @store(name: "mongo", collection: "orders") {
  id: ID!
  customerId: ID!
  total: Float!
}

A developer reading this sees that Customer.orders crosses a process boundary. In Hasura the equivalent fact lives in an OpenDD metadata file separate from the type definition. That difference — visible at the point of use versus separated for decoupling — is the entire design claim, and SC-6 is the test of it.

The honest counter-argument, stated in the proposal rather than discovered in review: coupling placement to the schema means a placement change is a schema change, which is exactly what the external-metadata design is protecting against. This project’s claim is narrow — that for small teams owning both concerns, visibility is worth more than decoupling — and the measurement may not support it.

### 6.4 Computational method and operation subset

Method family: rule-based query rewriting over a logical plan algebra, plus experimental measurement. Not machine learning; this is an empirical systems study.

GraphQL operation subset (MVA): single named query operation · field selection sets to depth 2 · one cross-store relationship traversal per operation · argument-based filtering with conjunctive comparison predicates (eq, lt, gt, lte, gte, in) · limit and offset · single-level aggregation (count, sum, avg, min, max) with grouping · named fragments.

Pushdown rules:

- Predicate pushdown — a filter argument referencing exactly one type is pushed to that type’s adapter and translated to native form: a WHERE clause for PostgreSQL, a $match stage for MongoDB.

- Projection pushdown (extension) — only fields referenced in the selection set, join keys, or residual predicates are requested from the backend.

- Limit pushdown — pushed only when the plan proves it order-safe; otherwise not pushed. Correctness dominates.

Join ordering (extension): heuristic, smallest-estimated-cardinality first, using per-type row counts from the placement map. No join-selectivity estimation.

Measurement statistics: median of 7 timed runs, 3 warm-up runs discarded, IQR reported with every median. Medians rather than means because query latency distributions are right-skewed and a single GC pause or page fault would dominate a mean.

Workload: adapted from the published Unibench multi-model benchmark rather than invented. This is a deliberate bias control (§9, R3) — a workload I design myself is a workload I can unconsciously shape to flatter my engine. Data placement follows Unibench’s natural entity model, not my convenience.

Evidence to submit: this method summary and its rationale, included in the proposal.

### 6.5 The measurement arms

Every workload query runs on all four floor arms, or the omission is recorded with a stated reason.

| Arm | Description |
| --- | --- |
| A1 | This engine, pushdown enabled |
| A2 | Consolidated PostgreSQL, all entities in one instance |
| A3 | Naive application-level federation: full fetches pulled into Python, joined in a loop |
| A4 | This engine, pushdown disabled |
| A5 (extension) | Hasura DDN over the same two backends |

### 6.6 API and integration plan

| Dependency | Version | Access route | Licence |
| --- | --- | --- | --- |
| PostgreSQL | 16.x | Docker image, pinned by digest | PostgreSQL Licence (permissive) |
| MongoDB Community | 7.x | Docker image, pinned by digest | SSPL |
| Redis (extension) | 7.x | Docker image | RSALv2 / SSPL dual |
| Neo4j Community (extension) | 5.x | Docker image | GPLv3 |
| graphql-core (parser) | 3.x | PyPI | MIT |
| psycopg | 3.x | PyPI | LGPL |
| pymongo | 4.x | PyPI | Apache-2.0 |
| Unibench workload + generator | [version] | [locate the repository and record the URL] | [verify licence before committing any generated data to a public repo] |
| Hasura DDN | current | Requires a Hasura Cloud account + DDN CLI + Docker | [verify current terms; confirm the free tier permits publishing comparative results] |
| pytest, pytest-cov | latest | PyPI | MIT |
| Docker Engine + Compose | latest | Local install | Apache-2.0 |

Access-readiness action: every _[verify]_ above must be resolved in WP-1 (Week 3) and the table updated in the repository. Any dependency still unverified at the midpoint hard stop is escalated to the supervisor.

Evidence to submit: this integration/dependency table with access-readiness and risk notes.

## 7. Project Plan

### 7.1 Phases and dependency order

The ordering constraint that matters most: the oracle is built before the benchmark, not after. A benchmark over an unverified engine measures the latency of wrong answers. This single dependency drives the shape of the whole plan.

The second constraint: the SC-6 counting protocol is written and committed before either system is measured. A protocol written after seeing one result is not a protocol.

P0 Approval
   │
   ▼
P1 Environment + data ──► P2 Schema annotation, resolver, parser
                              │
                              ▼
                          P3 Adapters + single-store execution
                              │
                              ▼
                          P4 Cross-store join
                              │
                              ▼
                          P5 Differential oracle ◄── hard gate: no timing run until green
                              │
                              ├──► P6 Pushdown ──► P7 Benchmark harness ──► P8 Sweep
                              │                                                 │
                              └──► P9 Configuration-complexity study            │
                                          │                                     │
                                          └──────────┬──────────────────────────┘
                                                     ▼
                                              P10 Analysis
                                                     │
                                                     ▼
                                              P11 Report + walkthrough

P9 runs in parallel with P6–P8 because it depends on the schema design being settled, not on the engine being fast. This is the only parallelism available in a solo project and it is deliberate — it means a benchmark slippage does not take the design result down with it.

### 7.2 Milestone schedule

| Milestone | Week | Gate criterion — what must be true to pass |
| --- | --- | --- |
| HS1 — Proposal approval | 2 | This package submitted; §11 decisions raised with the supervisor |
| M1 — Environment ready | 3 | Compose stack up; Unibench licence resolved; Hasura account verified; all _[verify]_ cells closed; parser choice made (ADR-0002) |
| M2 — Annotation design frozen | 3 | ADR-0003 records the @store syntax and the rejected alternatives |
| M3 — Data loaded, both placements | 4 | Federated placement and consolidated mirror provably equivalent (counts + checksums) |
| HS2 | [?] | Single-store queries executing end to end against both backends |
| M4 — Cross-store traversal works | 6 | Two-store relationship returns results; correctness not yet claimed |
| M5 — Oracle green | 7 | 100% agreement on the workload. Hard gate: no timing run before this passes |
| HS3 — Midpoint | [?] | MVA floor demonstrably reached; baseline measurement taken; §4 thresholds revised once and frozen; Decisions 1–3 resolved; IRB exemption obtained or the study extension cut |
| M6 — Predicate pushdown | 9 | Rules fire; byte counters instrumented; A4 arm available; oracle still green |
| M7 — Complexity protocol committed | 9 | eval/complexity/PROTOCOL.md in the repository, before either system is measured |
| HS4 | [?] | Benchmark harness runs all four arms unattended |
| M8 — Full measurement run | 12 | Complete parameter sweep; raw artifacts committed |
| HS5 | [?] | Crossover analysis and complexity results drafted |
| M9 — Reproducibility rehearsal | 13 | Clean checkout on a second machine reproduces the headline numbers |
| HS6 | [?] | Report draft complete |
| M10 — Freeze | 14 | Code frozen; no new features; defects triaged against SC-7 |
| HS7 — Final | [?] | Artifact, report, reproducibility package, recorded walkthrough |

### 7.3 Buffer

Weeks 11 and 13 carry no new feature work by design. They exist to absorb slippage. If nothing slips, they go to the report and the walkthrough rehearsal — never to scope.

## 8. Work Breakdown Structure

| WP | Work package | Weeks | Deliverable | Depends on | Criterion served |
| --- | --- | --- | --- | --- | --- |
| WP-0 | Proposal approval package | 2 | This document + the approval brief in §12 | — | SC-10 |
| WP-1 | Environment and dependency verification | 3 | Compose stack; dependency table closed; ADR-0002 (parser) | WP-0 | SC-9 |
| WP-2 | Schema annotation design + placement resolver | 3–4 | @store directive; resolver; validator; ADR-0003; plan-assertion tests | WP-1 | SC-2, SC-6 |
| WP-3 | Adapters and single-store execution | 4–5 | adapters/pg.py, adapters/mongo.py; conformance suite | WP-2 | SC-2 |
| WP-4 | Data loading, both placements | 4 | Loader; equivalence check (counts + checksums) | WP-1 | SC-1 |
| WP-5 | Cross-store hash join | 6 | Executor; two-store traversals returning results | WP-3, WP-4 | SC-2 |
| WP-6 | Differential oracle | 6–7 | oracle/; order-insensitive comparison; CI integration | WP-5 | SC-1 |
| WP-7 | Baseline measurement + threshold revision | 8 | Baseline report; §4 thresholds revised once and frozen | WP-6 | SC-4 |
| WP-8 | Predicate pushdown + byte instrumentation | 8–9 | Rewrite rules; adapter byte counters; A4 arm | WP-6 | SC-3 |
| WP-9 | Benchmark harness | 10 | bench/; four arms; run artifacts with config hash + hardware fingerprint | WP-8 | SC-4, SC-9 |
| WP-10 | Configuration-complexity study | 9–11 | eval/complexity/; protocol committed before measurement; both systems measured | WP-2 | SC-6 |
| WP-11 | Parameter sweep and full runs | 11–12 | Raw results committed; ≥6 points per curve | WP-9 | SC-5 |
| WP-12 | Reproducibility rehearsal | 13 | Clean-machine re-run; one-command documentation | WP-9 | SC-9 |
| WP-13 | Report | 13–14 | Report including threats to validity | WP-11, WP-10 | O8 |
| WP-14 | Recorded walkthrough | 14–15 | Recording per the rubric | WP-13 | — |
| E-1 | Projection pushdown | 10 | Extension rule | WP-8 | SC-3 |
| E-2 | Heuristic join ordering | 10 | Extension rule + ADR | WP-8 | SC-4 |
| E-3 | Redis adapter | 11 | Third adapter | WP-9 | SC-2 |
| E-4 | Neo4j adapter | 11 | Fourth adapter | E-3 | SC-2 |
| E-5 | Three-store traversals | 12 | Executor extension | E-3 | SC-2 |
| E-6 | Hasura as live measurement arm | 12 | A5 arm | WP-9 | SC-4 |
| E-7 | Developer usability study | 11–12 | Task protocol, N=8–12, time-on-task + error rate | WP-10, IRB exemption | SC-6 |

Extensions carry no dependent floor work. Cutting any one of them removes exactly one row.

## 9. Assumptions, Constraints, and Risks

### 9.1 Assumptions

| # | Assumption | If false |
| --- | --- | --- |
| A1 | The Unibench generator is obtainable and its licence permits academic use and publication of results | Substitute a documented synthetic generator on the published schema; record as a validity threat |
| A2 | A Hasura DDN free-tier account is obtainable and its terms permit publishing comparative measurements | Substitute locally-run GraphQL Mesh as the SC-6 comparator; declare the substitution |
| A3 | The development machine can be dedicated to benchmark runs for the required windows | Extend measurement windows; increase run count |
| A4 | The supervisor accepts a rigorously measured negative result as project success | Escalate immediately. Load-bearing — see §11, Decision 2 |
| A5 | Synthetic benchmark data only; no real, personal, or institutional data at any point | Trigger compliance review before proceeding |
| A6 | Read-only scope is acceptable for a graduate-level artifact | Renegotiate scope in Week 3, not Week 10 |
| A7 | Median-of-7 with warm-up discard adequately controls measurement noise on this hardware | Increase run count; report the revised protocol |
| A8 | Docker containers on one host do not distort relative timings across arms | Stated as a validity threat regardless; all arms share the same distortion |
| A9 | ~15 hours/week available | Cut extensions earlier. The MVA floor is sized for less |
| A10 | No employer intellectual property, code, data, or infrastructure is used at any point | Not negotiable. All data synthetic, all code original or permissively licensed |

### 9.2 Constraints

- Time: 14 weeks, fixed, with seven immovable hard stops.

- Personnel: solo. Only one parallel track exists (§7.1), everything else is serial.

- Hardware: one machine. No cluster, no cloud budget assumed beyond a free tier.

- Data: synthetic only.

- Scope: read-only, subset GraphQL, ≤4 backends.

- Licensing: project code released under a permissive licence; no copyleft dependency may be linked into distributed code.

### 9.3 Risk register

| ID | Risk | L | I | Mitigation | Residual |
| --- | --- | --- | --- | --- | --- |
| R1 | Scope creep. “One more backend, one more optimization” consumes the semester | High | High | MVA floor defined in advance (§5.1); extensions in a fixed cut order (§5.2); scope re-read at every hard stop | Med — requires ongoing discipline |
| R2 | Silent correctness bugs. Cross-store joins return plausible wrong answers, invalidating every measurement | Med | Critical | Oracle built at WP-6, before any timing run. Hard gate at M5. Oracle runs in CI on every commit | Low |
| R3 | Benchmark bias. I control the system, the workload, and the criteria, and I have an incentive for a positive result | High | High | Workload adapted from published Unibench, not invented. Thresholds pre-registered and revised exactly once, at the midpoint, before measurement. SC-6 counting protocol committed before either system is measured. All queries run on all arms or the omission is recorded with a reason. Raw timings, config hashes, hardware fingerprints committed. Plus the social mitigation: written supervisor agreement that a negative result is success | Med — revisited at each hard stop |
| R4 | Design-claim bias. SC-6 tests my own design idea, and I choose the task and the counting rules | High | High | Protocol committed before measurement (M7). Task drawn from Hasura’s own documented tutorial flow rather than invented. Both counts reported raw, not as a ratio only. The report states explicitly what a null result would look like | Med — inherent; disclosed rather than dissolved |
| R5 | Measurement noise on consumer hardware swamps the effect | Med | High | Median-of-7, warm-up discard, IQR with every median, documented isolation protocol. A crossing inside the IQR band is reported as indeterminate, not as a point | Low |
| R6 | Unibench unavailable or unlicensed | Med | Med | Resolved in Week 3, not Week 8. Fallback generator on the published schema, substitution declared | Low |
| R7 | External service risk: Hasura Cloud. Account, quota, or terms change mid-semester; terms may restrict published benchmarks | Med | Med | Verified in Week 3. GraphQL Mesh fallback identified. SC-6 is the only floor criterion depending on it | Low |
| R8 | Parser library mismatch — graphql-core does not expose directive metadata in a usable form | Med | Med | Evaluated Week 3; hand-written parser for the §6.4 subset as fallback, budgeted in WP-2 | Low |
| R9 | Environment drift — a version change mid-semester invalidates earlier runs | Low | High | Images pinned by digest; dependencies hash-locked; runtime versions recorded per run artifact | Low |
| R10 | Ethical: aggregation risk. Lowering the cost of cross-store joins makes re-identification across separated data sets cheaper. Data separation is itself a privacy control, and this project erodes it | Med | Med | Synthetic data only. The absence of an authorization model declared as a limitation in the report, not buried. The report states that the artifact must not be pointed at real personal data without an access-control layer this project does not provide. The same statement appears in the repository README, which matters more than the report because the repository is what people will actually use | Med — inherent to the problem, not removable |
| R11 | Ethical: no authorization model. A federation layer that bypasses per-store access controls is a security anti-pattern if deployed | Low (demo only) | High (if deployed) | Out of scope and stated as such (§5.3 #5). README carries an explicit not-for-production notice | Low |
| R12 | Human-subjects risk if the usability extension proceeds | Low | Med | Extension is contingent on written IRB exemption by the midpoint (§4.2). No participant data beyond task timings; no identifiers retained | Low |
| R13 | Reviewer objection: “why not just use Hasura?” | High | Med | Answered directly in §3.2 and in the report. The design variable cannot be varied inside a system that fixes it. Hasura appears as a comparator, which strengthens rather than undermines the result | Low |
| R14 | Competing coursework compresses available hours | Med | Med | Buffer weeks 11 and 13; extensions cut before floor work; hours tracked in the weekly journal | Med |
| R15 | Machine or data loss | Low | High | Git remote pushed at least daily; run artifacts committed, not held locally | Low |

### 9.4 Ethics, privacy, and compliance

No real, personal, or institutional data is used at any point. All benchmark data is synthetic. No employer code, data, or infrastructure is involved.

Two ethical issues survive scrutiny and are documented rather than dissolved, because neither is genuinely removable from a project of this kind: the aggregation risk in R10 and the absent authorization model in R11.

A third arises only if the usability extension proceeds. No human-subjects work will begin without written IRB exemption (§11, Decision 6); if exemption is not obtained by the midpoint hard stop, the extension is cut. Written confirmation is being requested rather than assumed for the base project as well.

## 10. Revision Record — Supervisor Feedback Substitute

Disclosure, stated plainly: I did not obtain instructor feedback on the Assignment 01 deliverable before preparing this package. The task list directs students to revise against that feedback. In its absence I conducted a structured self-review of the Week 1 charter against the Assignment 01 rubric criteria and revised against my own findings. This is a substitute for supervisor feedback, not an equivalent to it, and I am flagging it as such rather than presenting the revision as externally validated.

[If you do receive feedback before submitting, replace this section with the real thing — it will score better.]

| # | Weakness identified in charter v0.1 | Revision in v0.1 |
| --- | --- | --- |
| F1 | Prior art was addressed at the SQL-federation layer (Trino, Calcite) but not at the GraphQL layer, where the closest competitors actually sit. A reviewer aware of Hasura would have found the charter naive | §2.3 now addresses Hasura’s architecture directly, including its connector model and where it places placement information. §3.2 answers “why build rather than adopt” before it is asked |
| F2 | The contribution was purely empirical. With a strong incumbent in the same space, a measurement-only contribution is thin | §2.4 and §6.3 add a design claim with a stated counter-argument, and SC-6 makes it testable. The project now has two independent results, either of which can carry the semester |
| F3 | Success thresholds were deferred entirely to a later baseline. Defensible as method, but leaves the proposal with no decision-ready criteria — exactly what the rubric penalizes | §4 states ten criteria with thresholds, methods, and fallbacks, plus one documented revision point and a freeze thereafter |
| F4 | “Crossover” was the central claim but was never operationally defined. An undefined dependent variable cannot be measured | §4.1 defines it formally, names the independent variable, and specifies how an in-noise crossing is reported |
| F5 | The plan listed phases without explicit dependency order, obscuring the one ordering constraint that actually matters | §7.1 makes the oracle-before-benchmark dependency a hard gate at M5, and adds the protocol-before-measurement gate at M7 |
| F6 | The charter claimed no external-service dependencies. That was true then and is no longer true, and the rubric explicitly asks for this | §6.6 now includes Hasura Cloud with its own readiness state, risk row (R7), and named fallback |
| F7 | Dependency treatment was thin — tools named without licences, readiness, or fallbacks | §6.6 is a full table with licence, readiness, and a named fallback for every medium-or-higher-risk dependency. Unibench licensing escalated to a Week 3 blocker |
| F8 | The out-of-scope list omitted the write path, the single largest thing a reader would assume is included | §5.3 #1–2. Writes are now the first exclusion listed |
| F9 | Aggregation risk was identified as an ethical concern with no mitigation reaching the artifact itself | R10 now carries an artifact-level commitment: synthetic data only, plus an explicit not-for-production statement in the README, which is what people will actually read |
| F10 | No quality or defect criterion. The proposal could have been satisfied by working code with no test discipline | SC-7 and SC-8 added |
| F11 | No WBS mapping deliverables to weeks; issue-board intent described but not written down | §8 |
| F12 | Buffer was implicit. A 14-week solo plan with no declared slack is an optimistic plan | §7.3 declares weeks 11 and 13 as buffer, with a rule against spending them on scope |
| F13 | No stakeholder acceptance criterion, despite the rubric naming it | SC-10, tied to the §11 decisions with a defined escalation point |

## 11. Open Supervisor Decisions

The first three are blocking and should be resolved before the midpoint hard stop.

| # | Decision required | What it blocks |
| --- | --- | --- |
| 1 | Is the framing acceptable? The contribution is a design claim plus a measurement, not a competitive engine. If an architectural contribution competitive with existing systems is expected, I need to know now, not in Week 8 | Everything |
| 2 | Is a negative result acceptable as success? Requested in writing (§3.2, R3, R4) | Benchmark and study integrity |
| 3 | Is a local containerized demonstration sufficient as the final artifact, or is a deployment expected? | Architecture; several weeks of work |
| 4 | Provisional thresholds, revised once at the midpoint — acceptable, or are fixed criteria required in the approved proposal? | Proposal sign-off |
| 5 | Backend selection. PostgreSQL + MongoDB at the floor; Redis then Neo4j as extensions. Any preference, particularly if the graph case is considered more interesting than the key–value case? | WP-1, Week 3 |
| 6 | Compliance. Written confirmation that the base project requires no IRB submission, and guidance on the exemption path if the usability extension proceeds | Ethics closure; E-7 |
| 7 | Workload source. Unibench-derived rather than self-designed, for bias control. Acceptable, or is a different benchmark preferred? | WP-1, Week 3 |

## 12. One-Page Approval Brief

Project: Placement as Schema — a GraphQL federation layer that declares backend placement inside the type system, evaluated on both configuration complexity and the workload point at which federation stops paying relative to consolidation.

Student: [name] · Supervisor: [name] · Date: [date]

What it is. A read-only GraphQL federation engine over PostgreSQL and MongoDB, in which each type declares its backing store via a schema directive rather than in external metadata. Shipped with a differential correctness oracle, a four-arm benchmark harness, and a pre-registered configuration-complexity comparison against Hasura DDN. All measurements reproducible from a clean checkout.

Where the contribution sits. Two places. The design claim is that placement belongs where the developer can see it; existing systems separate the two for decoupling reasons, and this project tests whether that separation costs more than it saves for small teams. The empirical claim is a reproducible characterization of the federation-versus-consolidation crossover. The engine itself is apparatus — Hasura and Trino already do federation better than a solo student will, and the report says so.

What success looks like. Correctness verified against the oracle on 100% of the workload; ≥70% reduction in bytes transferred from predicate pushdown on selective queries; a crossover point reported with IQR bounds, or a substantiated finding that none exists in the tested range; a configuration-complexity result reported raw in both directions. A rigorously measured negative result on either claim is a success.

Minimum viable artifact. Two backends, the annotation and resolver, single- and two-store queries, predicate pushdown, the oracle, the comparison against consolidated PostgreSQL, and the complexity study. Everything else is an extension with a pre-declared cut order.

What remains conditional.

- Supervisor agreement on the framing in §3.2 — this is the one that could end the project and it should be settled this week.

- Written agreement that a negative result counts as success (§11 #2).

- Unibench licence verification — Week 3 blocker; fallback generator identified.

- Hasura Cloud account and terms verification — Week 3 blocker; GraphQL Mesh fallback identified.

- Parser library fit — Week 3 decision; hand-written fallback budgeted.

- Final success thresholds — provisional now, revised once at the midpoint, frozen after.

- IRB position in writing; the usability extension is cut if exemption is not obtained by the midpoint.

Evidence expected by the next checkpoint.

- Repository with the structure in §3.4, under version control, issues attached to milestones matching the seven hard-stop dates

- Docker Compose stack running both backends, images pinned by digest

- Dependency table (§6.6) with every readiness cell closed

- ADR-0002 (parser decision) and ADR-0003 (@store syntax, with rejected alternatives) committed

- Unibench licence question resolved either way, in writing

- Hasura Cloud access confirmed or the fallback triggered

- Week 3 journal entry with hours logged

- One single-store query executing end to end against at least one backend

Risk I am most worried about. Not technical difficulty. It is that I designed SC-6 to test my own idea, and I choose the task and the counting rules. The protocol-before-measurement commitment at M7 and the supervisor’s written acceptance of a negative result are the two mechanisms I am relying on, and both need supervisor visibility to work.

## 13. References

Eight sources; the assignment requires five. Author, title, venue, and year are given; verify pagination, DOIs, and formatting against your required style guide before submission. Do not submit these strings unchecked.

- Stonebraker, M., & Çetintemel, U. (2005). “‘One Size Fits All’: An Idea Whose Time Has Come and Gone.” Proceedings of the International Conference on Data Engineering (ICDE).

- Lu, J., & Holubová, I. (2019). “Multi-model Databases: A New Journey to Handle the Variety of Data.” ACM Computing Surveys.

- Duggan, J., et al. (2015). “The BigDAWG Polystore System.” ACM SIGMOD Record.

- Begoli, E., et al. (2018). “Apache Calcite: A Foundational Framework for Optimized Query Processing Over Heterogeneous Data Sources.” Proceedings of SIGMOD.

- Kolev, B., et al. (2016). “CloudMdsQL: Querying Heterogeneous Cloud Data Stores with a Common Language.” Distributed and Parallel Databases.

- Zhang, C., & Lu, J. (2021). “Holistic Evaluation in Multi-Model Databases Benchmarking.” Distributed and Parallel Databases. — the Unibench workload.

- Hartig, O., & Pérez, J. (2018). “Semantics and Complexity of GraphQL.” Proceedings of the World Wide Web Conference. — the formal semantics underpinning the operation subset in §6.4.

- Hasura. Native Data Connector Specification and Hasura DDN architecture documentation. — primary source for §2.3. [Record the access date and exact URLs.]